## INTRODUCTION
AN INTRODUCTION TO MAKING SUSTAINABLE CHANGE
SETTING THE STAGE
Making sustainable change does not have to be a daunting task; as even the smallest change can reap big benefits in patient care and employee morale. Whether you are the facility Quality Improvement Coordinator or if you have no idea what healthcare quality is, this workbook is designed to walk with you through one of the simplest but most powerful tools to implement change...The Model for Improvement. The Model for Improvement spans all industries and works with changes of all sizes. By working through the Model for Improvement method to drill down to the root of the problem, brainstorm ideas and put those ideas into play; you will bring about long lasting and foundational change. This workbook provides a roadmap to implementing a change, along with additional resources and tools that you can use as you get more comfortable!
BEFORE YOU GET STARTED
Before you get started, consider the following: 1. Involve colleagues that are hands on doing the work. This is essential for meaningful change and will also provide the best input and ideas. 2. Start small. Like microscopic small. Example: You want to test a new documentation tool. Test with one nurse and one patient. Did that work well? Test with 2 nurses and 2 shifts and 5 patients. Keep broadening incrementally to catch any issues or changes that need to be made.
THE MODEL FOR IMPROVEMENT
STEP 1: THREE QUESTIONS
There are THREE QUESTIONS to ask to develop improvement projects. 1. What are we trying to accomplish? 2. How will we know that change is an improvement? 3. What changes can we make that will result in an improvement?
STEP 2: PLANNING & TESTING
You have heard the saying "If you fail to plan, you will plan to fail." This is true especially in making changes. If you don't have a plan or a direction, it is difficult to identify what to do, how to do it, and how to know if the change was positive. PDSA is an acronym for Plan, Do, Study, Act; and is tool for testing and documenting ideas of change. PDSA is typically completed in cycles commonly called the PDSA Cycle as the process is repeated multiple times as change ideas are tested and tweaked based on experiences. PDSA allows teams to put ideas into practice and test them prior to implementation to learn what works and what doesn't. Tests should start on a small scale and then broaden. PLAN: What is your plan to test your idea for changes? Who will do what, where, when, how many times? DO: Carrying out your test. STUDY: Observe and learn. After the first test is carried out do a quick huddle with stakeholders and team members and dish on what went well and what didn't. ACT: Take Action. Are you going to Adapt the test, Adopt the test, or Abandon the test?
CLICK HERE FOR WORKBOOK INSTRUCTIONS
Workbook developed by: | Development Resources
Jennifer Wagner, CPHQ | Katrina Strowbridge, PI Manager, Clark Fork Valley Hospital
Copyright © 2021 Jennifer Wagner, CPHQ. All Rights Reserved. | IHI Model for Improvement
http://www.ihi.org/resources/Pages/HowtoImprove/default.aspx
QAPI PDSA Cycle Template
https://www.cms.gov/medicare/provider-enrollment-and-certification/qapi/downloads/pdsacycledebedits.pdf
The Essential Guide to PDSA: Models, Worksheets, and Templates
https://www.smartsheet.com/content/plan-do-study-act-guide

## INSTRUCTIONS
HOW TO USE THIS WORKBOOK
1. Read the 'INTRODUCTION' tab to familiarize yourself with the process of making sustainable changes and a high overview of the tools and concepts included in this workbook.
CLICK HERE TO ACCESS THE 'INTRODUCTION' TAB
2. Save this template as a new document so you can complete content for your specific project.
To save as a new document, click on File > Save As. When prompted save the new document to your preferred location and change the document name to identify the project.
3. Start with answering the 3 Questions to frame your work in the '3 QUESTIONS' tab.
CLICK HERE TO ACCESS THE '3 QUESTIONS' TAB
4. In the 'PROJECT SUMMARY' tab; fill in the details in Summary and Plan sections. This will help organize thoughts, ideas, and goals of the project.
CLICK HERE TO ACCESS THE 'PROJECT SUMMARY' TAB
5. Develop first PDSA Cycle. Remember, you might do the PDSA process more than one time so if there is more than one cycle, a 'Cycle Template' tab is provide and can be copied for each cycle.
CLICK HERE TO ACCESS THE 'PDSA CYCLE 1' TAB
More than one cycle? Follow these instructions to copy the CYCLE TEMPLATE. Right Click on the CYCLE TEMPLATE tab and select Move and Copy. A Move or Copy dialogue box will open. Select Project Summary in the Before Sheet list then check the Make a Copy box. Select OK. Rename the tab by right clicking and selecting rename.
6. Repeat as needed.
ADVANCED TIP: Add additional tabs to this workbook for developed tools, data, and other information relevant to the project to help keep everything in one place!
LOOK FOR
Boxes like this to provide extra guidance and prompts!

## RESOURCES
ADDITIONAL TOOLS, TEMPLATES AND RESOURCES
7 BASIC QUALITY TOOLS - TEMPLATES - RESOURCES
American Society for Quality | https://asq.org/quality-resources/seven-basic-quality-tools
OTHER QUALITY SUPPORT RESOURCES
IHI Model for Improvement | http://www.ihi.org/resources/Pages/HowtoImprove/default.aspx
QAPI PDSA Cycle Template | https://www.cms.gov/medicare/provider-enrollment-and-certification/qapi/downloads/pdsacycledebedits.pdf
The Essential Guide to PDSA: Models, Worksheets, and Templates | https://www.smartsheet.com/content/plan-do-study-act-guide
SWOT Analysis (Strengths, Weaknesses, Opportunities, Threats) | https://www.liveplan.com/blog/what-is-a-swot-analysis-and-how-to-do-it-right-with-examples/
AIMS & GOALS
S.M.A.R.T Goal Setting | Atlassian Work life Blog
IDEAS
Define Current Steps of the Process (Process Mapping) | Agency for Healthcare Research and Quality
American Society for Quality
Define Cause of Errors or Issues (Root Cause Analysis) | Institute for Healthcare Quality Improvement at UNC
American Society for Quality
Identify Possible Issues (Failure Mode & Effect Analysis) | American Society for Quality

## 3 QUESTIONS
THE 3 QUESTIONS
These questions guide improvement work.
QUESTION 1
AIM/GOAL | What are we trying to accomplish?
S | Specific
M | Measurable
A | Achievable
R | Relevant
T | Time-bound
AIM STATEMENT: After identifying the SMART elements, write your Aim/Goal here. See box to the left for additional guidance.
QUESTION 2
MEASURES | How will we know that change is an improvement?
QUESTION 3
IDEAS | What changes can we make that will result in an improvement?
QUESTION 1
Write in SMART Goal format.
Bolded components should be included in Aim Statement.
Formula:
Our goal is to [quantifiable objective] by [timeframe or deadline]. [Key players or teams] will accomplish this goal by [what steps you’ll take to achieve the goal]. Accomplishing this goal will [result or benefit].
QUESTION 2
Describe the measurable outcomes you want to see.
QUESTION 3
See Resources Tab for information and templates.
Define the process currently in place with process mapping or flow charting.
Identify opportunities for improvement. Use tools like Root Cause or Failure Mode & Effect Analysis.
  Points where breakdowns occur
  Work-a-rounds that have been developed
  Variations that occur.
  Duplicate or unnecessary steps
Decide what you will change and determine interventions based on analysis
  Identify better ways to do something that address the root cause of the problem.
  Learn what has worked at other organizations or by high performers.
  Review best available evidence for what works is.

## PROJECT SUMMARY
PDSA
PROJECT SUMMARY
PROJECT START DATE: |  |  |  | PROJECT COMPLETION DATE:
PROJECT TITLE |  | Test
PROJECT LEAD
TEAM MEMBERS
PLAN What exactly are we going to do??
This indicator or project supports ("X" all that apply):
Quality Assurance |  |  | Quality Control |  | Performance Improvement
High Risk |  |  | Improved Health Outcome |  | Transitions of care, including readmissions
High volume |  |  | Hospital Quality Objective |  | Prevention/reduction of adverse events
Problem Prone |  |  |  |  | Prevention/reduction of hosp. acquired conditions
Other |  |  |  |  | Prevention/reduction of medical errors
BACKGROUND: Why is this important? What are the issues? What questions do you want to answer?
PLAN & GOAL: What is the project goal? What issues is to be addressed? What do you predict will happen? What resources will be needed? What data will be collected?
IDEAS: What ideas/change concepts will drive completion of the project aim?
Option 1: Enter your ideas in the space below.
Option 2: Complete Driver Diagram Template worksheet and include ideas in the table below. | [5 empty] | Link to Driver Diagram Template
Idea/Change Concept |  |  | Process Measure |  | Goal
Need more space? Right click on blank row above, choose copy, then insert copied cells.
START CYCLE #1
CYCLE SUMMARIES (OPTIONAL)
CYCLE NUMBER | GOAL |  |  |  | GOAL MET? | ADAPT/ADOPT/ABANDON
1
Need more space? Right click on blank row above, choose copy, then insert copied cells.
What is a Driver Diagram?
A driver diagram is a visual display of a team’s theory of what “drives,” or contributes to, the achievement of a project aim. This clear picture of a team’s shared view is a useful tool for communicating to a range of stakeholders where a team is testing and working.
(Institute for Healthcare Improvement)
There are two options for developing ideas. The first would be just a simple brainstorm and conversation as a team. The second, slightly more advanced, would be using a Driver Diagram Tool.
Cycle Summaries
This is completely optional! If you'd like to have an at-a-glance look at the status/progression of your cycles, you can play with completing this section!

## DRIVER DIAGRAM
DRIVER DIAGRAM TEMPLATE
| AIM | PRIMARY DRIVERS | SECONDARY DRIVERS | SPECIFIC IDEAS TO TEST OR CHANGE CONCEPTS
| AIM | PRIMARY DRIVERS | SECONDARY DRIVERS | SPECIFIC IDEAS TO TEST OR CHANGE CONCEPTS
| GOAL What will be improved, by how much, for whom, and by when. See "Plan & Goal" of Project Summary tab. | FACTORS Most significant and high level influencers on the Aim. | FACTORS Influencers of primary drivers. These can connect to more than one primary driver. | CHANGE IDEAS Specific ideas to influence change. This will build your "DO". These also can connect to more than one secondary driver.
Copy this template as needed!

## PDSA CYCLE 1
NAVIGATE TO SECTIONS (click to navigate to phase of the cycle)
| PLAN |  |  | DO |  |  | STUDY |  |  | ACT
PDSA CYCLE
PROJECT SUMMARY
PROJECT TITLE | #VALUE!
CYCLE NO. | 1 | Is this cycle used to: |  |  | X | Develop an idea for change
Test an idea for change
Implement an idea for change
PLAN: What exactly are we going to do?
PLAN & GOAL: This will automatically fill from the PROJECT SUMMARY tab. Do not delete the formula.
0
DATA & MEASUREMENT: Use answers from Question 2 of "Three Questions"
Data Collection Frequency: |  |  |  | <--- | select from drop down
Who is collecting data? |  |  |  | What resources is the data coming from?
Numerator Description:
Denominator Description:
How will data be collected? |  |  |  | Check Sheet |  |  | Data Collection Form
|  |  |  | Interviews |  |  | Run Charts
|  |  |  | Flow Charts |  |  | Written Surveys
|  |  |  | Swim Lane Maps |  |  | Root Cause Analysis/FMEA
Other
Results Reported to (check all): |  |  |  | P & T |  |  | AC/ER/OB
|  |  |  | ISPC |  |  | OB
|  |  |  | Med Staff |  |  | Clinic Providers
|  |  |  | OR/Trauma |  |  | UR
Other
DO
Who will do what, when, and where to implement the plan and change concepts noted above?
WHAT |  |  |  | WHO |  | WHEN |  | NOTES/COMPLETED?
Need more space? Right click on blank row above, choose copy, then insert copied cells.
Was the cycle carried out as planned? General Observations? Problems/Challenges? Unintended outcomes?
STUDY
Special Note: While data collection is essential to determine if your change is an improvement, this may not be the format meant for you and that is okay! You can design how you would like to study your data. Regardless how you measure your data, complete compare and interpret sections to practice evaluation of data.
* Enter data collection date on the DATE row. * As data is collected per the collection schedule identified, enter the Numerator (N=) and Denominator (D=). * Enter Goal/Targets and Benchmark in the first column. Following columns will automatically populate. * Rates will automatically calculate and display on the graph below.
Measure:
DATE
Numerator
Denominator
Rate | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Goal or Target |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Benchmark |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMPARE TO PREDICTIONS: Did you achieve what you wanted? How did actual results compare to predictions?
INTERPRET YOUR DATA: What does the data show? Did the change lead to improvement? Are there implications or unintended consequences?
ACT
ADAPT, ADOPT, ABANDON - "X" ONE
ADAPT |  | We will modify the plan and repeat PDSA cycle on same scale with changes.
ADOPT |  | We will implement and spread the change strategy across our program. Final PDSA cycle after plans have been tested under wide test conditions.
ABANDON |  | We will stop testing and move to a new change strategy. Start fresh.
ADAPT or ADOPT? Copy "Cycle Template" tab and rename to next cycle number. Repeat the same process.
This will be your first PDSA Cycle. If you have additional cycles, you can copy the CYCLE TEMPLATE. Subsequent cycles would either be Test or Implement.
More than one measure?
1. Select rows starting at the one above date and continuing to below the graph.
2. Right click + Copy
3. Click on first row below graph.
4. Right click + Insert copied cells.
5. Click on new graph.
6. Right click + Select Data
7. Expand Chart Range and select the range with Rate, Goal or Target, and Benchmark that was just copied.
8. Repeat for each measure
*If more than one graph, you may add a chart title with the measure using these instructions.
1. Click on graph.
2. Click on green + to the right for Chart Elements.
3. Check Chart Title.
4. In the chart, edit the text to reflect the measure name/description.
Copy a Excel Tab
1. Right click on the tab.
2. Choose Move or Copy.
3. Select what sheet you would like your copy to be placed in front of via Before Sheet section.
4. Select Make a Copy via the checkbox under the sheet list.
5. Rename tab. Right click and select Rename.
6. To help with navigation, you can change the tab color to align with the topic/section of the workbook. Right click and select Tab Color.

## CYCLE TEMPLATE
NAVIGATE TO SECTIONS (click to navigate to phase of the cycle)
| PLAN |  |  | DO |  |  | STUDY |  |  | ACT
PDSA CYCLE
PROJECT SUMMARY
PROJECT TITLE | #VALUE!
CYCLE NO. |  | Is this cycle used to: |  |  |  | Develop an idea for change
Test an idea for change
Implement an idea for change
PLAN: What exactly are we going to do?
PLAN & GOAL: This will automatically fill from the PROJECT SUMMARY tab. Do not delete the formula.
0
DATA & MEASUREMENT: Use answers from Question 2 of "Three Questions"
Data Collection Frequency: |  |  |  | <--- | select from drop down
Who is collecting data? |  |  |  | What resources is the data coming from?
Numerator Description:
Denominator Description:
How will data be collected? |  |  |  | Check Sheet |  |  | Data Collection Form
|  |  |  | Interviews |  |  | Run Charts
|  |  |  | Flow Charts |  |  | Written Surveys
|  |  |  | Swim Lane Maps |  |  | Root Cause Analysis/FMEA
Other
Results Reported to (check all): |  |  |  | P & T |  |  | AC/ER/OB
|  |  |  | ISPC |  |  | OB
|  |  |  | Med Staff |  |  | Clinic Providers
|  |  |  | OR/Trauma |  |  | UR
Other
DO
Who will do what, when, and where to implement the plan and change concepts noted above?
WHAT |  |  |  | WHO |  | WHEN |  | NOTES/COMPLETED?
Need more space? Right click on blank row above, choose copy, then insert copied cells.
Was the cycle carried out as planned? General Observations? Problems/Challenges? Unintended outcomes?
STUDY
Special Note: While data collection is essential to determine if your change is an improvement, this may not be the format meant for you and that is okay! You can design how you would like to study your data. Regardless how you measure your data, complete compare and interpret sections to practice evaluation of data.
* Enter data collection date on the DATE row. * As data is collected per the collection schedule identified, enter the Numerator (N=) and Denominator (D=). * Enter Goal/Targets and Benchmark in the first column. Following columns will automatically populate. * Rates will automatically calculate and display on the graph below.
Measure:
DATE
Numerator
Denominator
Rate | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Goal or Target |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Benchmark |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMPARE TO PREDICTIONS: Did you achieve what you wanted? How did actual results compare to predictions?
INTERPRET YOUR DATA: What does the data show? Did the change lead to improvement? Are there implications or unintended consequences?
ACT
ADAPT, ADOPT, ABANDON - "X" ONE
ADAPT |  | We will modify the plan and repeat PDSA cycle on same scale with changes.
ADOPT |  | We will implement and spread the change strategy across our program. Final PDSA cycle after plans have been tested under wide test conditions.
ABANDON |  | We will stop testing and move to a new change strategy. Start fresh.
ADAPT or ADOPT? Copy "Cycle Template" tab and rename to next cycle number. Repeat the same process.
This will be your first PDSA Cycle. If you have additional cycles, you can copy the CYCLE TEMPLATE. Subsequent cycles would either be Test or Implement.
More than one measure?
1. Select rows starting at the one above date and continuing to below the graph.
2. Right click + Copy
3. Click on first row below graph.
4. Right click + Insert copied cells.
5. Click on new graph.
6. Right click + Select Data
7. Expand Chart Range and select the range with Rate, Goal or Target, and Benchmark that was just copied.
8. Repeat for each measure
*If more than one graph, you may add a chart title with the measure using these instructions.
1. Click on graph.
2. Click on green + to the right for Chart Elements.
3. Check Chart Title.
4. In the chart, edit the text to reflect the measure name/description.
Copy a Excel Tab
1. Right click on the tab.
2. Choose Move or Copy.
3. Select what sheet you would like your copy to be placed in front of via Before Sheet section.
4. Select Make a Copy via the checkbox under the sheet list.
5. Rename tab. Right click and select Rename.
6. To help with navigation, you can change the tab color to align with the topic/section of the workbook. Right click and select Tab Color.

## POSTER PRESENTATION INFORMATION
Send hospital logo to Jen:
Project Title:
Project Team Members, QI Lead/Coach:
Introduction:
What was your aim, and why was this important to work on?
Objectives:
Tests of Change:
What are the ideas that your team tested and implemented.
Materials & Methods
Provide driver diagram or other tools and methods used.
Did you involved patient/families or staff in this work? How?
Results:
Share your data and stories.
Conculsions:
What have you learnt from this Project?
Did you see an improvement?
What is the impact?
Any next steps or progression?

## LookUps (hidden)
Data Collection Frequency | Yes/No | Action
Daily | Yes | Adapt
Weekly | No | Adopt
Monthly |  | Abandon
Quarterly
Other