CCM Program Build Checklist

Program Setup

☐ Create CCM job description (RN, LPN, MA, or Care Coordinator role)

☐ Hire and/or designate staff for CCM

☐ Train staff on Medicare CCM requirements (billing, documentation)

☐ Establish a supervising provider and oversight process

Policies & Forms

☐ Develop a CCM patient consent form (or customize an existing one)

☐ Review clinic’s patient assistance/financial policy for CCM copays

☐ Create policy for enrollment, disenrollment, and patient refusal

EHR & Documentation

☐ Ensure a care plan template exists in the EHR (customize if needed)

☐ Set up a CCM documentation note

☐ Create workflows for medication reconciliation and care gap reviews

☐ Build a consistent EMR flag or tag for enrolled CCM patients

Patient Identification & Enrollment

☐ Generate an eligible patient list (2+ chronic conditions, ≥12 months expected)

☐ Develop a process to review eligibility lists regularly (e.g., at huddles)

☐ Train front desk/MA staff to introduce CCM at check-in or AWVs

☐ Implement workflow for obtaining and scanning consent into chart

☐ Set enrollment targets (e.g., 5–10 new patients per provider per week)

Care Management Workflows

☐ Establish a standard workflow for monthly CCM touches (calls, chart review, etc.)

☐ Define productivity expectations (e.g., 5 new patients/day for new CCM staff)

☐ Incorporate CCM into morning huddles to flag opportunities

☐ Develop transition of care (TOC) and hospital follow-up process

☐ Standardize frequency of medication reconciliation (e.g., 3x/year for high-risk)

Billing & Finance

☐ Confirm billing workflows with revenue cycle staff (CPT 99490, 99439, 99487, 99489)

☐ Set up billing compliance checks to ensure CMS requirements are met

☐ Track claims paid vs. denied, and monitor revenue by provider/clinic

☐ Run a break-even analysis (patients needed to cover staff costs)

Program Monitoring

☐ Assign a “data champion” to pull CCM reports from EHR/claims

☐ Monitor enrollment vs. eligible population

☐ Track touches completed, care gaps closed, and patient outcomes

☐ Review financial performance monthly (claims submitted, paid, copays collected)

☐ Hold regular team meetings to review progress and barriers

Sustainability & Growth

☐ Build a growth plan (enrollment goals, staff expansion, outreach strategy)

☐ Tie CCM metrics to clinic quality/value-based programs (ACO, MIPS, pay-for-performance)

☐ Gather patient success stories to share with leadership and staff

☐ Develop a succession/back-up plan for CCM staff to ensure continuity

☐ Update templates, workflows, and policies annually for compliance changes